## HotFixes (hidden)
SEM Hot-Fix
|  | Implementation | Testing | Due date | Notes
SEM 3.5.0 Hot-Fix 1 | support for CISCO IPS v7.X from LMI, starting from LSP #19 | 100% | 100% | 2011-04-01 | sent to the support for publication on SaleForces
SEM 3.5.0 Hot-Fix 2 | bug fixed in the log collector for syslog TCP listener | 100% | 100% | 2011-04-01 | sent to the support for publication on SaleForces
SEM 3.5.1 Hot-Fix 1 | support for CISCO IPS v7.X from LMI, starting from LSP #19 | 100% | 100% | 2011-04-01 | sent to the support for publication on SaleForces
SEM 3.5.0 Hot-Fix 3 | Bugs fixed in this hot-fix: * 26493 - Use of AES instead of 3DES cipher suite option in Tomcat * 27233 - Wrong rules are deleted from correlation scenarios * 26934 - GUI access is intermittent * 27928 - Update via the site update.exaprotect.com doesn't work | 100% | 100% | 2011-06-30
SEM 3.5.1 Hot-Fix 3 | Bugs fixed in this hot-fix: * 26493 - Use of AES instead of 3DES cipher suite option in Tomcat * 27233 - Wrong rules are deleted from correlation scenarios * 26934 - GUI access is intermittent * 27928 - Update via the site update.exaprotect.com doesn't work | 100% | 100% | 2011-06-30

## FastTrack (hidden)
FastTrack Projects
Project | Customer | Start | Target | % Complete | Notes
UC 2.0.1 AIX version | Barclays | 2011-01-04 | 2011-01-31 | 100% | Uploaded to support site.
SEM HA 3.5.1 | CNAF | 2011-01-05 | 2011-01-31 | 100% | Uploaded to support site for limited availability
Checkpoint VSX support | Hartford | 2011-01-04 | 2011-01-31 | 100% | Uploaded to support site.
SDEE Collector Enhancement | Exxon Mobile | 2011-05-09 | 2011-06-06 | 100% | Handed off to support today

## LSP23 Snapshot (hidden)
Project Name: | LSP 23 |  |  | 2011 |  | 2012 | [12 empty] | 2012 | [12 empty] | 2012 | [12 empty] | 2012
Product Manager: | Christophe Briguet |  |  | Q3 | Q4 | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
Project Manager: | Chris Otto |  |  |  |  | Jan |  |  |  | FEB |  |  |  | MAR |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
Overall |  | 50% | time axis 2012-01-06 to 2012-12-28
•Tentative Support for LMI 5.1.x, 5.2.x & 5.3•Cisco NetFlowPhase III, ESA (Ironport Mail Security),NX-OS(Nexus), IOS v15: Phase I•Windows 2008 German: Phase I•TrendMicro Control Manager v5.5•McAfee ePO v4.6 Stretch Goals:•Sourcefire Defense Center: Phase I (search)•VMWare vShield Edge: Phase II {Agile Reports}•VMWare vCloud Director v1.5•Juniper SSL VPN SA ver. 6.5.x/7.0•Juniper SSL VPN SA version 7.1 |  | Design | 100%
|  | Documentation | 0%
|  | Implementation | 70% |  | DEV | bar: 2012-01-06 to 2012-01-13
|  | Testing | 40% |  | QA | bar: 2012-01-06 to 2012-01-13
|  | Alpha | 90%
BETA
Release Notes | bar: 2012-02-24
RC
Release ( GA) | bar: 2012-03-30
Project Health Report
Weekly Status: On track Issue: N/A Risk: N/A

## Sheet1
Status | RoadMap Target | Type | Project Name | Product Owner | Program/Project Manager | GA Date | Year | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[8 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Approved |  | Project | Google | John | Mary |  | 2012 | bar: Q1 Mar
Approved |  | Project | Foswiki | Mary | John |  | 2012 | bar: Q2 Apr
Approved |  | Project |  |  |  |  | 2012 | bar: Q1 Mar
Approved |  | Project |  |  |  |  | 2012 | bar: Q2 Apr
Approved |  | Project |  |  |  |  | 2012 | bar: Q2 May
Delay |  | HOTFIX |  |  |  |  | 2012 | bar: Q1 Feb
OnHold |  | Project |  |  |  |  | 2012 | bar: Q1 Feb
|  | Project |  |  |  |  | 2012
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | 2012
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | N/A
|  | Project |  |  |  |  | 2012
|  | Project |  |  |  |  | 2012
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | 2012
|  | Project |  |  |  |  | 2013
|  | Project |  |  |  |  | 2013
Project
Fast Track
Fast Track